## Summary
field | value
schedule_name | Summer Schedule
schedule_start_date | 2026-06-01
work_on_weekends | FALSE
target_end_day | 20
current_day | 1
finish_day | 1
finish_date | Monday June 01, 2026
met_deadline | TRUE
total_planned_hours | 4.64
completed_hours_before_run | 0
remaining_hours_at_start | 4.64
total_used_hours | 4.64
remaining_backlog_hours | 0
recommendation_status | ON TRACK
bottleneck_type | None
available_backlog_hours | 4.64
blocked_backlog_hours | 0
total_backlog_hours | 4.64
capacity_to_deadline_hours | 540
extra_staff_days_needed | 0
recommended_action | Start-of-run backlog fits within available productive capacity before the deadline.

## Days
day | work_date | active_school_name | status_note | effective_staff | general_staff | carpet_staff | general_capacity | carpet_capacity | daily_capacity | general_used_capacity | carpet_used_capacity | used_capacity | general_unused_capacity | carpet_unused_capacity | unused_capacity | work_items
1 | Monday June 01, 2026 | WES | General crew working WES; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 4.64 | 0 | 4.64 | 22.36 | 0 | 22.36 | 3

## WorkLog
day | work_date | crew_type | school_name | building_name | zone_name | room_name | phase_name | available_day | hours_done | note
1 | Monday June 01, 2026 | General | WES | Main | Classrooms | Room 1 | Deep Clean | 1 | 2.17
1 | Monday June 01, 2026 | General | WES | Main | Classrooms | Room 1 | Strip | 1 | 0.99
1 | Monday June 01, 2026 | General | WES | Main | Classrooms | Room 1 | Wax (3 coats) | 1 | 1.48

## Tasks
school_name | building_name | zone_name | room_name | phase_name | available_day | available_date | total_hours | remaining_hours | status | notes
WES | Main | Classrooms | Room 1 | Deep Clean | 1 | Monday June 01, 2026 | 2.17 | 0 | Complete
WES | Main | Classrooms | Room 1 | Strip | 1 | Monday June 01, 2026 | 0.99 | 0 | Complete
WES | Main | Classrooms | Room 1 | Wax (3 coats) | 1 | Monday June 01, 2026 | 1.48 | 0 | Complete

## TimeBlocks
day | work_date | start_time | end_time | type | label | minutes | active_school_name
1 | Monday June 01, 2026 | 7:45 AM | 9:55 AM | work | Deep Clean - Room 1 (WES) | 130 | WES
1 | Monday June 01, 2026 | 9:55 AM | 10:00 AM | work | Strip - Room 1 (WES) | 5 | WES
1 | Monday June 01, 2026 | 10:00 AM | 10:15 AM | break | Break | 15 | WES
1 | Monday June 01, 2026 | 10:15 AM | 11:09 AM | work | Strip - Room 1 (WES) | 54 | WES
1 | Monday June 01, 2026 | 11:09 AM | 12:00 PM | work | Wax (3 coats) - Room 1 (WES) | 51 | WES
1 | Monday June 01, 2026 | 12:00 PM | 12:30 PM | lunch | Lunch | 30 | WES
1 | Monday June 01, 2026 | 12:30 PM | 1:08 PM | work | Wax (3 coats) - Room 1 (WES) | 38 | WES