## Summary
Field | Value
Schedule Name | Summer Schedule
Schedule Start Date | 2026-06-15
Target End Date | 2026-07-31
Work On Weekends | FALSE
Paid Holidays In Range | 2
Target End Day | 33
Current Day | 1
Projected Finish Day | 32
Projected Finish Date | Tuesday July 28, 2026
Deadline Met | TRUE
Export Scope | All Sites
Filtered Total Planned Hours | 801.71
Filtered Total Used Hours | 801.71
Filtered Remaining Backlog Hours | 0
Recommendation Status | ON TRACK WITH ACCESS CONSTRAINTS
Bottleneck Type | Room Availability
Recommended Action | Schedule is on track, but later room release is controlling part of the finish. Earlier access would create a smoother schedule faster than adding staff.

## Days
Workday Number | Work Date | Active Site | Day Note | Effective Staff | Cleaning Staff | Carpet Staff | Cleaning Capacity Hours | Carpet Capacity Hours | Total Capacity Hours | Used Hours | Unused Hours | Matching Work Items
1 | Monday June 15, 2026 | Wright | General crew working Wright; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 27 | 0 | 13
2 | Tuesday June 16, 2026 | Wright | General crew working Wright; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 27 | 0 | 14
3 | Wednesday June 17, 2026 | Wright | General crew working Wright; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 26.76 | 0.24 | 8
4 | Thursday June 18, 2026 | Wright | General crew working Wright; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 26.97 | 0.03 | 14
5 | Friday June 19, 2026 | Wright | General crew working Wright; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 26.03 | 0.97 | 13
6 | Monday June 22, 2026 | Wright | General crew working Wright; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 25.37 | 1.63 | 5
7 | Tuesday June 23, 2026 | Wright | General crew working Wright; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 26.19 | 0.81 | 9
8 | Wednesday June 24, 2026 | Wright | General crew working Wright; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 25.82 | 1.18 | 9
9 | Thursday June 25, 2026 | Wright | General crew working Wright; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 20.79 | 6.21 | 7
10 | Friday June 26, 2026 | Wright | General crew idle; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 25.1 | 1.9 | 2
11 | Monday June 29, 2026 | RL Stevens | General crew working RL Stevens; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 27 | 0 | 7
12 | Tuesday June 30, 2026 | RL Stevens | General crew working RL Stevens; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 27 | 0 | 11
13 | Wednesday July 01, 2026 | RL Stevens | General crew working RL Stevens; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 27 | 0 | 14
14 | Thursday July 02, 2026 | RL Stevens | General crew working RL Stevens; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 26.95 | 0.05 | 12
15 | Friday July 03, 2026 | RL Stevens | General crew working RL Stevens; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 26.37 | 0.63 | 6
16 | Monday July 06, 2026 | RL Stevens | General crew working RL Stevens; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 26.95 | 0.05 | 12
17 | Tuesday July 07, 2026 | RL Stevens | General crew working RL Stevens; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 26.89 | 0.11 | 10
18 | Wednesday July 08, 2026 | RL Stevens | General crew working RL Stevens; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 25.57 | 1.43 | 2
19 | Thursday July 09, 2026 | RL Stevens | General crew working RL Stevens; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 25.84 | 1.16 | 7
20 | Friday July 10, 2026 | RL Stevens | General crew working RL Stevens; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 26.34 | 0.66 | 8
21 | Monday July 13, 2026 | RL Stevens | General crew working RL Stevens; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 25.47 | 1.53 | 8
22 | Tuesday July 14, 2026 | RL Stevens | General crew idle; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 5.92 | 21.08 | 2
23 | Wednesday July 15, 2026 | JX Wilson | General crew working available rooms at JX Wilson while blocked rooms are deferred; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 27 | 0 | 13
24 | Thursday July 16, 2026 | JX Wilson | General crew working JX Wilson; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 26.86 | 0.14 | 9
25 | Friday July 17, 2026 | JX Wilson | General crew working JX Wilson; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 26.44 | 0.56 | 12
26 | Monday July 20, 2026 | JX Wilson | General crew working JX Wilson; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 25.6 | 1.4 | 6
27 | Tuesday July 21, 2026 | JX Wilson | General crew working JX Wilson; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 26.11 | 0.89 | 9
28 | Wednesday July 22, 2026 | JX Wilson | General crew idle; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 23.7 | 3.3 | 2
29 | Thursday July 23, 2026 | JX Wilson | General crew cleaning deferred rooms at JX Wilson; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 27 | 0 | 13
30 | Friday July 24, 2026 | JX Wilson | General crew cleaning deferred rooms at JX Wilson; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 26.67 | 0.33 | 14
31 | Monday July 27, 2026 | JX Wilson | General crew cleaning deferred rooms at JX Wilson; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 25.93 | 1.07 | 9
32 | Tuesday July 28, 2026 | JX Wilson | General crew idle; no carpet staff reserved today. | 4 | 4 | 0 | 27 | 0 | 27 | 12.06 | 14.94 | 4

## Work Log
Workday Number | Work Date | Crew Type | Site | Building | Zone | Room | Task | Available Day | Hours Done | Notes
1 | Monday June 15, 2026 | General | Wright | Elementary | Classrooms | Room 02 | Deep Clean | 1 | 2.1
1 | Monday June 15, 2026 | General | Wright | Elementary | Classrooms | Room 03 | Deep Clean | 1 | 2.17
1 | Monday June 15, 2026 | General | Wright | Elementary | Classrooms | Room 04 | Deep Clean | 1 | 2.17
1 | Monday June 15, 2026 | General | Wright | Elementary | Classrooms | Room 05 | Deep Clean | 1 | 2.17
1 | Monday June 15, 2026 | General | Wright | Elementary | Classrooms | Room 06 | Deep Clean | 1 | 2.17
1 | Monday June 15, 2026 | General | Wright | Elementary | Classrooms | Room 07 | Deep Clean | 1 | 2.17
1 | Monday June 15, 2026 | General | Wright | Elementary | Classrooms | Room 08 | Deep Clean | 1 | 2.17
1 | Monday June 15, 2026 | General | Wright | Elementary | Classrooms | Room 09 | Deep Clean | 1 | 2.17
1 | Monday June 15, 2026 | General | Wright | Elementary | Classrooms | Room 10 | Deep Clean | 1 | 2.17
1 | Monday June 15, 2026 | General | Wright | Elementary | Classrooms | Room 11 | Deep Clean | 1 | 2.17
1 | Monday June 15, 2026 | General | Wright | Elementary | Classrooms | Room 12 | Deep Clean | 1 | 2.17
1 | Monday June 15, 2026 | General | Wright | Elementary | Classrooms | Room 13 | Deep Clean | 1 | 2.17
1 | Monday June 15, 2026 | General | Wright | Elementary | Classrooms | Room 14 | Deep Clean | 1 | 1.03
2 | Tuesday June 16, 2026 | General | Wright | Elementary | Classrooms | Room 14 | Deep Clean | 1 | 1.14
2 | Tuesday June 16, 2026 | General | Wright | Elementary | Classrooms | Room 15 | Deep Clean | 1 | 2.17
2 | Tuesday June 16, 2026 | General | Wright | Elementary | Classrooms | Room 16 | Deep Clean | 1 | 2.02
2 | Tuesday June 16, 2026 | General | Wright | Elementary | Classrooms | Room 17 | Deep Clean | 1 | 2.1
2 | Tuesday June 16, 2026 | General | Wright | Elementary | Classrooms | Room 18 | Deep Clean | 1 | 2.17
2 | Tuesday June 16, 2026 | General | Wright | Elementary | Classrooms | Room 20 | Deep Clean | 1 | 2.17
2 | Tuesday June 16, 2026 | General | Wright | Elementary | Classrooms | Room 21 | Deep Clean | 1 | 2.1
2 | Tuesday June 16, 2026 | General | Wright | Elementary | Classrooms | Room 22 | Deep Clean | 1 | 2.17
2 | Tuesday June 16, 2026 | General | Wright | Elementary | Classrooms | Room 23 | Deep Clean | 1 | 2.17
2 | Tuesday June 16, 2026 | General | Wright | Elementary | Classrooms | Room 24 | Deep Clean | 1 | 2.17
2 | Tuesday June 16, 2026 | General | Wright | Elementary | Classrooms | Room 25 | Deep Clean | 1 | 2.17
2 | Tuesday June 16, 2026 | General | Wright | Elementary | Classrooms | Room 26 | Deep Clean | 1 | 2.17
2 | Tuesday June 16, 2026 | General | Wright | Elementary | Classrooms | Room 27 | Deep Clean | 1 | 2.17
2 | Tuesday June 16, 2026 | General | Wright | MPR | MPR | New Gym | Deep Clean | 1 | 0.06
3 | Wednesday June 17, 2026 | General | Wright | MPR | MPR | New Gym | Deep Clean | 1 | 7.74
3 | Wednesday June 17, 2026 | General | Wright | MPR | Kitchen | Kitchen | Deep Clean | 1 | 2.19
3 | Wednesday June 17, 2026 | General | Wright | Main Office Building | Classrooms | Room 1 | Deep Clean | 1 | 2.1
3 | Wednesday June 17, 2026 | General | Wright | Main Office Building | Classrooms | Room K | Deep Clean | 1 | 2.94
3 | Wednesday June 17, 2026 | General | Wright | Main Office Building | Office | Main Office | Deep Clean | 1 | 4.59
3 | Wednesday June 17, 2026 | General | Wright | Old MPR | MPR | Old Gym | Deep Clean | 1 | 4.75
3 | Wednesday June 17, 2026 | General | Wright | Old MPR | Kitchen | Old Kitchen | Deep Clean | 1 | 1.16
3 | Wednesday June 17, 2026 | General | Wright | Main Office Building | Classrooms | Room K | Strip | 1 | 1.3
4 | Thursday June 18, 2026 | General | Wright | Elementary | Classrooms | Room 02 | Strip | 1 | 1.88
4 | Thursday June 18, 2026 | General | Wright | Elementary | Classrooms | Room 03 | Strip | 1 | 1.94
4 | Thursday June 18, 2026 | General | Wright | Elementary | Classrooms | Room 04 | Strip | 1 | 1.94
4 | Thursday June 18, 2026 | General | Wright | Elementary | Classrooms | Room 05 | Strip | 1 | 1.94
4 | Thursday June 18, 2026 | General | Wright | Elementary | Classrooms | Room 06 | Strip | 1 | 1.94
4 | Thursday June 18, 2026 | General | Wright | Elementary | Classrooms | Room 07 | Strip | 1 | 1.94
4 | Thursday June 18, 2026 | General | Wright | Elementary | Classrooms | Room 08 | Strip | 1 | 1.94
4 | Thursday June 18, 2026 | General | Wright | Elementary | Classrooms | Room 09 | Strip | 1 | 1.94
4 | Thursday June 18, 2026 | General | Wright | Elementary | Classrooms | Room 10 | Strip | 1 | 1.94
4 | Thursday June 18, 2026 | General | Wright | Elementary | Classrooms | Room 11 | Strip | 1 | 1.94
4 | Thursday June 18, 2026 | General | Wright | Elementary | Classrooms | Room 12 | Strip | 1 | 1.94
4 | Thursday June 18, 2026 | General | Wright | Elementary | Classrooms | Room 13 | Strip | 1 | 1.94
4 | Thursday June 18, 2026 | General | Wright | Elementary | Classrooms | Room 14 | Strip | 1 | 1.94
4 | Thursday June 18, 2026 | General | Wright | Elementary | Classrooms | Room 16 | Strip | 1 | 1.81
5 | Friday June 19, 2026 | General | Wright | Elementary | Classrooms | Room 15 | Strip | 1 | 1.94
5 | Friday June 19, 2026 | General | Wright | Elementary | Classrooms | Room 17 | Strip | 1 | 1.88
5 | Friday June 19, 2026 | General | Wright | Elementary | Classrooms | Room 18 | Strip | 1 | 1.94
5 | Friday June 19, 2026 | General | Wright | Elementary | Classrooms | Room 20 | Strip | 1 | 1.94
5 | Friday June 19, 2026 | General | Wright | Elementary | Classrooms | Room 21 | Strip | 1 | 1.88
5 | Friday June 19, 2026 | General | Wright | Elementary | Classrooms | Room 22 | Strip | 1 | 1.94
5 | Friday June 19, 2026 | General | Wright | Elementary | Classrooms | Room 23 | Strip | 1 | 1.94
5 | Friday June 19, 2026 | General | Wright | Elementary | Classrooms | Room 24 | Strip | 1 | 1.94
5 | Friday June 19, 2026 | General | Wright | Elementary | Classrooms | Room 25 | Strip | 1 | 1.94
5 | Friday June 19, 2026 | General | Wright | Elementary | Classrooms | Room 26 | Strip | 1 | 1.94
5 | Friday June 19, 2026 | General | Wright | Elementary | Classrooms | Room 27 | Strip | 1 | 1.94
5 | Friday June 19, 2026 | General | Wright | MPR | Kitchen | Kitchen | Strip | 1 | 2.92
5 | Friday June 19, 2026 | General | Wright | Main Office Building | Classrooms | Room 1 | Strip | 1 | 1.88
6 | Monday June 22, 2026 | General | Wright | MPR | MPR | New Gym | Strip | 1 | 10.4
6 | Monday June 22, 2026 | General | Wright | Old MPR | MPR | Old Gym | Strip | 1 | 6.33
6 | Monday June 22, 2026 | General | Wright | Elementary | Classrooms | Room 02 | Wax (3 coats) | 1 | 2.81
6 | Monday June 22, 2026 | General | Wright | Elementary | Classrooms | Room 03 | Wax (3 coats) | 1 | 2.91
6 | Monday June 22, 2026 | General | Wright | Elementary | Classrooms | Room 04 | Wax (3 coats) | 1 | 2.91
7 | Tuesday June 23, 2026 | General | Wright | Elementary | Classrooms | Room 05 | Wax (3 coats) | 1 | 2.91
7 | Tuesday June 23, 2026 | General | Wright | Elementary | Classrooms | Room 06 | Wax (3 coats) | 1 | 2.91
7 | Tuesday June 23, 2026 | General | Wright | Elementary | Classrooms | Room 07 | Wax (3 coats) | 1 | 2.91
7 | Tuesday June 23, 2026 | General | Wright | Elementary | Classrooms | Room 08 | Wax (3 coats) | 1 | 2.91
7 | Tuesday June 23, 2026 | General | Wright | Elementary | Classrooms | Room 09 | Wax (3 coats) | 1 | 2.91
7 | Tuesday June 23, 2026 | General | Wright | Elementary | Classrooms | Room 10 | Wax (3 coats) | 1 | 2.91
7 | Tuesday June 23, 2026 | General | Wright | Elementary | Classrooms | Room 11 | Wax (3 coats) | 1 | 2.91
7 | Tuesday June 23, 2026 | General | Wright | Elementary | Classrooms | Room 12 | Wax (3 coats) | 1 | 2.91
7 | Tuesday June 23, 2026 | General | Wright | Elementary | Classrooms | Room 13 | Wax (3 coats) | 1 | 2.91
8 | Wednesday June 24, 2026 | General | Wright | Elementary | Classrooms | Room 14 | Wax (3 coats) | 1 | 2.91
8 | Wednesday June 24, 2026 | General | Wright | Elementary | Classrooms | Room 15 | Wax (3 coats) | 1 | 2.91
8 | Wednesday June 24, 2026 | General | Wright | Elementary | Classrooms | Room 16 | Wax (3 coats) | 1 | 2.71
8 | Wednesday June 24, 2026 | General | Wright | Elementary | Classrooms | Room 17 | Wax (3 coats) | 1 | 2.81
8 | Wednesday June 24, 2026 | General | Wright | Elementary | Classrooms | Room 18 | Wax (3 coats) | 1 | 2.92
8 | Wednesday June 24, 2026 | General | Wright | Elementary | Classrooms | Room 20 | Wax (3 coats) | 1 | 2.92
8 | Wednesday June 24, 2026 | General | Wright | Elementary | Classrooms | Room 21 | Wax (3 coats) | 1 | 2.81
8 | Wednesday June 24, 2026 | General | Wright | Elementary | Classrooms | Room 22 | Wax (3 coats) | 1 | 2.92
8 | Wednesday June 24, 2026 | General | Wright | Elementary | Classrooms | Room 23 | Wax (3 coats) | 1 | 2.92
9 | Thursday June 25, 2026 | General | Wright | Elementary | Classrooms | Room 24 | Wax (3 coats) | 1 | 2.92
9 | Thursday June 25, 2026 | General | Wright | Elementary | Classrooms | Room 25 | Wax (3 coats) | 1 | 2.92
9 | Thursday June 25, 2026 | General | Wright | Elementary | Classrooms | Room 26 | Wax (3 coats) | 1 | 2.92
9 | Thursday June 25, 2026 | General | Wright | Elementary | Classrooms | Room 27 | Wax (3 coats) | 1 | 2.92
9 | Thursday June 25, 2026 | General | Wright | MPR | Kitchen | Kitchen | Wax (3 coats) | 1 | 4.38
9 | Thursday June 25, 2026 | General | Wright | Main Office Building | Classrooms | Room 1 | Wax (3 coats) | 1 | 2.81
9 | Thursday June 25, 2026 | General | Wright | Main Office Building | Classrooms | Room K | Wax (3 coats) | 1 | 1.94
10 | Friday June 26, 2026 | General | Wright | MPR | MPR | New Gym | Wax (3 coats) | 1 | 15.6
10 | Friday June 26, 2026 | General | Wright | Old MPR | MPR | Old Gym | Wax (3 coats) | 1 | 9.5
11 | Monday June 29, 2026 | General | RL Stevens | Building A | Classrooms | Room 03 | Deep Clean | 1 | 1.96
11 | Monday June 29, 2026 | General | RL Stevens | Building A | Office | Admin Office | Deep Clean | 1 | 2.15
11 | Monday June 29, 2026 | General | RL Stevens | Building A | Staff | Staff Room | Deep Clean | 1 | 2.97
11 | Monday June 29, 2026 | General | RL Stevens | Building B | Classrooms | K1 | Deep Clean | 1 | 3.22
11 | Monday June 29, 2026 | General | RL Stevens | Building B | Classrooms | K2 | Deep Clean | 1 | 3.45
11 | Monday June 29, 2026 | General | RL Stevens | Building B | Library | Library | Deep Clean | 1 | 3.28
11 | Monday June 29, 2026 | General | RL Stevens | Building C | MPR | MPR | Deep Clean | 1 | 9.98
12 | Tuesday June 30, 2026 | General | RL Stevens | Building C | MPR | MPR | Deep Clean | 1 | 1.78
12 | Tuesday June 30, 2026 | General | RL Stevens | Building C | Kitchen | Kitchen | Deep Clean | 1 | 2.72
12 | Tuesday June 30, 2026 | General | RL Stevens | Building D | Classrooms | Room 14 | Deep Clean | 1 | 2.54
12 | Tuesday June 30, 2026 | General | RL Stevens | Building D | Classrooms | Room 15 | Deep Clean | 1 | 2.54
12 | Tuesday June 30, 2026 | General | RL Stevens | Building D | Classrooms | Room 16 | Deep Clean | 1 | 2.54
12 | Tuesday June 30, 2026 | General | RL Stevens | Building D | Classrooms | Room 17 | Deep Clean | 1 | 2.54
12 | Tuesday June 30, 2026 | General | RL Stevens | Building D | Classrooms | Room 18 | Deep Clean | 1 | 2.54
12 | Tuesday June 30, 2026 | General | RL Stevens | Building D | Classrooms | Room 19 | Deep Clean | 1 | 2.54
12 | Tuesday June 30, 2026 | General | RL Stevens | Building E | Classrooms | Room 08 | Deep Clean | 1 | 2.54
12 | Tuesday June 30, 2026 | General | RL Stevens | Building E | Classrooms | Room 09 | Deep Clean | 1 | 2.54
12 | Tuesday June 30, 2026 | General | RL Stevens | Building E | Classrooms | Room 10 | Deep Clean | 1 | 2.2
13 | Wednesday July 01, 2026 | General | RL Stevens | Building E | Classrooms | Room 10 | Deep Clean | 1 | 0.34
13 | Wednesday July 01, 2026 | General | RL Stevens | Building E | Classrooms | Room 11 | Deep Clean | 1 | 2.54
13 | Wednesday July 01, 2026 | General | RL Stevens | Building E | Classrooms | Room 12 | Deep Clean | 1 | 2.62
13 | Wednesday July 01, 2026 | General | RL Stevens | Building E | Classrooms | Room 13 | Deep Clean | 1 | 2.54
13 | Wednesday July 01, 2026 | General | RL Stevens | Building F | Classrooms | Room 04 | Deep Clean | 1 | 2.54
13 | Wednesday July 01, 2026 | General | RL Stevens | Building F | Classrooms | Room 05 | Deep Clean | 1 | 2.54
13 | Wednesday July 01, 2026 | General | RL Stevens | Building F | Classrooms | Room 06 | Deep Clean | 1 | 2.54
13 | Wednesday July 01, 2026 | General | RL Stevens | Building F | Classrooms | Room 07 | Deep Clean | 1 | 2.54
13 | Wednesday July 01, 2026 | General | RL Stevens | Building H | Classrooms | Room 20 | Deep Clean | 1 | 2.33
13 | Wednesday July 01, 2026 | General | RL Stevens | Building H | Classrooms | Room 21 | Deep Clean | 1 | 1.81
13 | Wednesday July 01, 2026 | General | RL Stevens | Building H | Classrooms | Room 22 | Deep Clean | 1 | 2.25
13 | Wednesday July 01, 2026 | General | RL Stevens | Building H | Office | Conference Room 1 | Deep Clean | 1 | 0.71
13 | Wednesday July 01, 2026 | General | RL Stevens | Building H | Office | Conference Room 2 | Deep Clean | 1 | 0.68
13 | Wednesday July 01, 2026 | General | RL Stevens | Building I | Classrooms | K3 | Deep Clean | 1 | 1.04
14 | Thursday July 02, 2026 | General | RL Stevens | Building I | Classrooms | K3 | Deep Clean | 1 | 1.21
14 | Thursday July 02, 2026 | General | RL Stevens | Building I | Classrooms | K4 | Deep Clean | 1 | 2.25
14 | Thursday July 02, 2026 | General | RL Stevens | Building J | Classrooms | Room 01 | Deep Clean | 1 | 2.33
14 | Thursday July 02, 2026 | General | RL Stevens | Building J | Classrooms | Room 02 | Deep Clean | 1 | 2.25
14 | Thursday July 02, 2026 | General | RL Stevens | Building J | Classrooms | Room 25 | Deep Clean | 1 | 2.17
14 | Thursday July 02, 2026 | General | RL Stevens | Building A | Classrooms | Room 03 | Strip | 1 | 1.75
14 | Thursday July 02, 2026 | General | RL Stevens | Building A | Staff | Staff Room | Strip | 1 | 1.96
14 | Thursday July 02, 2026 | General | RL Stevens | Building B | Classrooms | K1 | Strip | 1 | 2.88
14 | Thursday July 02, 2026 | General | RL Stevens | Building B | Classrooms | K2 | Strip | 1 | 3.08
14 | Thursday July 02, 2026 | General | RL Stevens | Building B | Library | Library | Strip | 1 | 1.37
14 | Thursday July 02, 2026 | General | RL Stevens | Building C | Kitchen | Kitchen | Strip | 1 | 3.63
14 | Thursday July 02, 2026 | General | RL Stevens | Building H | Classrooms | Room 20 | Strip | 1 | 2.08
15 | Friday July 03, 2026 | General | RL Stevens | Building C | MPR | MPR | Strip | 1 | 15.68
15 | Friday July 03, 2026 | General | RL Stevens | Building D | Classrooms | Room 14 | Strip | 1 | 2.27
15 | Friday July 03, 2026 | General | RL Stevens | Building D | Classrooms | Room 15 | Strip | 1 | 2.27
15 | Friday July 03, 2026 | General | RL Stevens | Building D | Classrooms | Room 16 | Strip | 1 | 2.27
15 | Friday July 03, 2026 | General | RL Stevens | Building D | Classrooms | Room 17 | Strip | 1 | 2.27
15 | Friday July 03, 2026 | General | RL Stevens | Building H | Classrooms | Room 21 | Strip | 1 | 1.62
16 | Monday July 06, 2026 | General | RL Stevens | Building D | Classrooms | Room 18 | Strip | 1 | 2.27
16 | Monday July 06, 2026 | General | RL Stevens | Building D | Classrooms | Room 19 | Strip | 1 | 2.27
16 | Monday July 06, 2026 | General | RL Stevens | Building E | Classrooms | Room 08 | Strip | 1 | 2.27
16 | Monday July 06, 2026 | General | RL Stevens | Building E | Classrooms | Room 09 | Strip | 1 | 2.27
16 | Monday July 06, 2026 | General | RL Stevens | Building E | Classrooms | Room 10 | Strip | 1 | 2.27
16 | Monday July 06, 2026 | General | RL Stevens | Building E | Classrooms | Room 11 | Strip | 1 | 2.27
16 | Monday July 06, 2026 | General | RL Stevens | Building E | Classrooms | Room 12 | Strip | 1 | 2.34
16 | Monday July 06, 2026 | General | RL Stevens | Building E | Classrooms | Room 13 | Strip | 1 | 2.27
16 | Monday July 06, 2026 | General | RL Stevens | Building F | Classrooms | Room 04 | Strip | 1 | 2.27
16 | Monday July 06, 2026 | General | RL Stevens | Building F | Classrooms | Room 05 | Strip | 1 | 2.27
16 | Monday July 06, 2026 | General | RL Stevens | Building F | Classrooms | Room 06 | Strip | 1 | 2.27
16 | Monday July 06, 2026 | General | RL Stevens | Building J | Classrooms | Room 25 | Strip | 1 | 1.94
17 | Tuesday July 07, 2026 | General | RL Stevens | Building F | Classrooms | Room 07 | Strip | 1 | 2.27
17 | Tuesday July 07, 2026 | General | RL Stevens | Building H | Classrooms | Room 22 | Strip | 1 | 2.01
17 | Tuesday July 07, 2026 | General | RL Stevens | Building I | Classrooms | K3 | Strip | 1 | 2.01
17 | Tuesday July 07, 2026 | General | RL Stevens | Building I | Classrooms | K4 | Strip | 1 | 2.01
17 | Tuesday July 07, 2026 | General | RL Stevens | Building J | Classrooms | Room 01 | Strip | 1 | 2.08
17 | Tuesday July 07, 2026 | General | RL Stevens | Building J | Classrooms | Room 02 | Strip | 1 | 2.01
17 | Tuesday July 07, 2026 | General | RL Stevens | Building A | Classrooms | Room 03 | Wax (3 coats) | 1 | 2.62
17 | Tuesday July 07, 2026 | General | RL Stevens | Building A | Staff | Staff Room | Wax (3 coats) | 1 | 2.95
17 | Tuesday July 07, 2026 | General | RL Stevens | Building B | Classrooms | K1 | Wax (3 coats) | 1 | 4.31
17 | Tuesday July 07, 2026 | General | RL Stevens | Building B | Classrooms | K2 | Wax (3 coats) | 1 | 4.62
18 | Wednesday July 08, 2026 | General | RL Stevens | Building B | Library | Library | Wax (3 coats) | 1 | 2.06
18 | Wednesday July 08, 2026 | General | RL Stevens | Building C | MPR | MPR | Wax (3 coats) | 1 | 23.52
19 | Thursday July 09, 2026 | General | RL Stevens | Building C | Kitchen | Kitchen | Wax (3 coats) | 1 | 5.44
19 | Thursday July 09, 2026 | General | RL Stevens | Building D | Classrooms | Room 14 | Wax (3 coats) | 1 | 3.4
19 | Thursday July 09, 2026 | General | RL Stevens | Building D | Classrooms | Room 15 | Wax (3 coats) | 1 | 3.4
19 | Thursday July 09, 2026 | General | RL Stevens | Building D | Classrooms | Room 16 | Wax (3 coats) | 1 | 3.4
19 | Thursday July 09, 2026 | General | RL Stevens | Building D | Classrooms | Room 17 | Wax (3 coats) | 1 | 3.4
19 | Thursday July 09, 2026 | General | RL Stevens | Building D | Classrooms | Room 18 | Wax (3 coats) | 1 | 3.4
19 | Thursday July 09, 2026 | General | RL Stevens | Building D | Classrooms | Room 19 | Wax (3 coats) | 1 | 3.4
20 | Friday July 10, 2026 | General | RL Stevens | Building E | Classrooms | Room 08 | Wax (3 coats) | 1 | 3.4
20 | Friday July 10, 2026 | General | RL Stevens | Building E | Classrooms | Room 09 | Wax (3 coats) | 1 | 3.4
20 | Friday July 10, 2026 | General | RL Stevens | Building E | Classrooms | Room 10 | Wax (3 coats) | 1 | 3.4
20 | Friday July 10, 2026 | General | RL Stevens | Building E | Classrooms | Room 11 | Wax (3 coats) | 1 | 3.4
20 | Friday July 10, 2026 | General | RL Stevens | Building E | Classrooms | Room 12 | Wax (3 coats) | 1 | 3.51
20 | Friday July 10, 2026 | General | RL Stevens | Building E | Classrooms | Room 13 | Wax (3 coats) | 1 | 3.4
20 | Friday July 10, 2026 | General | RL Stevens | Building F | Classrooms | Room 04 | Wax (3 coats) | 1 | 3.4
20 | Friday July 10, 2026 | General | RL Stevens | Building H | Classrooms | Room 21 | Wax (3 coats) | 1 | 2.43
21 | Monday July 13, 2026 | General | RL Stevens | Building F | Classrooms | Room 05 | Wax (3 coats) | 1 | 3.4
21 | Monday July 13, 2026 | General | RL Stevens | Building F | Classrooms | Room 06 | Wax (3 coats) | 1 | 3.4
21 | Monday July 13, 2026 | General | RL Stevens | Building F | Classrooms | Room 07 | Wax (3 coats) | 1 | 3.4
21 | Monday July 13, 2026 | General | RL Stevens | Building H | Classrooms | Room 20 | Wax (3 coats) | 1 | 3.12
21 | Monday July 13, 2026 | General | RL Stevens | Building H | Classrooms | Room 22 | Wax (3 coats) | 1 | 3.01
21 | Monday July 13, 2026 | General | RL Stevens | Building I | Classrooms | K3 | Wax (3 coats) | 1 | 3.01
21 | Monday July 13, 2026 | General | RL Stevens | Building I | Classrooms | K4 | Wax (3 coats) | 1 | 3.01
21 | Monday July 13, 2026 | General | RL Stevens | Building J | Classrooms | Room 01 | Wax (3 coats) | 1 | 3.12
22 | Tuesday July 14, 2026 | General | RL Stevens | Building J | Classrooms | Room 02 | Wax (3 coats) | 1 | 3.01
22 | Tuesday July 14, 2026 | General | RL Stevens | Building J | Classrooms | Room 25 | Wax (3 coats) | 1 | 2.91
23 | Wednesday July 15, 2026 | General | JX Wilson | Building 17-19 | Classrooms | Room 18 | Deep Clean | 1 | 2.25
23 | Wednesday July 15, 2026 | General | JX Wilson | Building 17-19 | Classrooms | Room 19 | Deep Clean | 1 | 2.1
23 | Wednesday July 15, 2026 | General | JX Wilson | Building 20-22 & 27 | Classrooms | Room 20 | Deep Clean | 1 | 2.17
23 | Wednesday July 15, 2026 | General | JX Wilson | Building 20-22 & 27 | Classrooms | Room 21 | Deep Clean | 1 | 2.17
23 | Wednesday July 15, 2026 | General | JX Wilson | Building 20-22 & 27 | Classrooms | Room 22 | Deep Clean | 1 | 2.1
23 | Wednesday July 15, 2026 | General | JX Wilson | Building 20-22 & 27 | Classrooms | Room 27 | Deep Clean | 1 | 2.1
23 | Wednesday July 15, 2026 | General | JX Wilson | Building 23-26 | Classrooms | Room 23 | Deep Clean | 1 | 2.66
23 | Wednesday July 15, 2026 | General | JX Wilson | Building 23-26 | Classrooms | Room 24 | Deep Clean | 1 | 1.96
23 | Wednesday July 15, 2026 | General | JX Wilson | Building 23-26 | Classrooms | Room 25 | Deep Clean | 1 | 2.03
23 | Wednesday July 15, 2026 | General | JX Wilson | Building 23-26 | Classrooms | Room 26 | Deep Clean | 1 | 1.96
23 | Wednesday July 15, 2026 | General | JX Wilson | Main Building | Classrooms | Room 01 | Deep Clean | 1 | 2.4
23 | Wednesday July 15, 2026 | General | JX Wilson | Main Building | Classrooms | Room 03 | Deep Clean | 1 | 2.4
23 | Wednesday July 15, 2026 | General | JX Wilson | Main Building | Classrooms | Room 04 | Deep Clean | 1 | 0.69
24 | Thursday July 16, 2026 | General | JX Wilson | Main Building | Classrooms | Room 04 | Deep Clean | 1 | 1.72
24 | Thursday July 16, 2026 | General | JX Wilson | Main Building | Office | Main Office | Deep Clean | 1 | 2.57
24 | Thursday July 16, 2026 | General | JX Wilson | Main Building | Office | Principal Office | Deep Clean | 1 | 0.89
24 | Thursday July 16, 2026 | General | JX Wilson | Multipurpose | MPR | MPR | Deep Clean | 1 | 8.35
24 | Thursday July 16, 2026 | General | JX Wilson | Multipurpose | Kitchen | Kitchen | Deep Clean | 1 | 1.05
24 | Thursday July 16, 2026 | General | JX Wilson | Staff & Kinder | Staff | Staff Rooms | Deep Clean | 1 | 7
24 | Thursday July 16, 2026 | General | JX Wilson | Building 17-19 | Classrooms | Room 18 | Strip | 1 | 2.01
24 | Thursday July 16, 2026 | General | JX Wilson | Building 17-19 | Classrooms | Room 19 | Strip | 1 | 1.88
24 | Thursday July 16, 2026 | General | JX Wilson | Multipurpose | Kitchen | Kitchen | Strip | 1 | 1.4
25 | Friday July 17, 2026 | General | JX Wilson | Building 20-22 & 27 | Classrooms | Room 20 | Strip | 1 | 1.94
25 | Friday July 17, 2026 | General | JX Wilson | Building 20-22 & 27 | Classrooms | Room 21 | Strip | 1 | 1.94
25 | Friday July 17, 2026 | General | JX Wilson | Building 20-22 & 27 | Classrooms | Room 22 | Strip | 1 | 1.88
25 | Friday July 17, 2026 | General | JX Wilson | Building 20-22 & 27 | Classrooms | Room 27 | Strip | 1 | 1.88
25 | Friday July 17, 2026 | General | JX Wilson | Building 23-26 | Classrooms | Room 23 | Strip | 1 | 2.38
25 | Friday July 17, 2026 | General | JX Wilson | Building 23-26 | Classrooms | Room 24 | Strip | 1 | 1.75
25 | Friday July 17, 2026 | General | JX Wilson | Building 23-26 | Classrooms | Room 25 | Strip | 1 | 1.81
25 | Friday July 17, 2026 | General | JX Wilson | Building 23-26 | Classrooms | Room 26 | Strip | 1 | 1.75
25 | Friday July 17, 2026 | General | JX Wilson | Main Building | Classrooms | Room 01 | Strip | 1 | 2.15
25 | Friday July 17, 2026 | General | JX Wilson | Main Building | Classrooms | Room 03 | Strip | 1 | 2.15
25 | Friday July 17, 2026 | General | JX Wilson | Main Building | Classrooms | Room 04 | Strip | 1 | 2.15
25 | Friday July 17, 2026 | General | JX Wilson | Staff & Kinder | Staff | Staff Rooms | Strip | 1 | 4.67
26 | Monday July 20, 2026 | General | JX Wilson | Multipurpose | MPR | MPR | Strip | 1 | 11.13
26 | Monday July 20, 2026 | General | JX Wilson | Building 17-19 | Classrooms | Room 18 | Wax (3 coats) | 1 | 3.01
26 | Monday July 20, 2026 | General | JX Wilson | Building 17-19 | Classrooms | Room 19 | Wax (3 coats) | 1 | 2.81
26 | Monday July 20, 2026 | General | JX Wilson | Building 20-22 & 27 | Classrooms | Room 20 | Wax (3 coats) | 1 | 2.92
26 | Monday July 20, 2026 | General | JX Wilson | Building 20-22 & 27 | Classrooms | Room 21 | Wax (3 coats) | 1 | 2.92
26 | Monday July 20, 2026 | General | JX Wilson | Building 20-22 & 27 | Classrooms | Room 22 | Wax (3 coats) | 1 | 2.81
27 | Tuesday July 21, 2026 | General | JX Wilson | Building 20-22 & 27 | Classrooms | Room 27 | Wax (3 coats) | 1 | 2.81
27 | Tuesday July 21, 2026 | General | JX Wilson | Building 23-26 | Classrooms | Room 23 | Wax (3 coats) | 1 | 3.56
27 | Tuesday July 21, 2026 | General | JX Wilson | Building 23-26 | Classrooms | Room 24 | Wax (3 coats) | 1 | 2.62
27 | Tuesday July 21, 2026 | General | JX Wilson | Building 23-26 | Classrooms | Room 25 | Wax (3 coats) | 1 | 2.72
27 | Tuesday July 21, 2026 | General | JX Wilson | Building 23-26 | Classrooms | Room 26 | Wax (3 coats) | 1 | 2.62
27 | Tuesday July 21, 2026 | General | JX Wilson | Main Building | Classrooms | Room 01 | Wax (3 coats) | 1 | 3.22
27 | Tuesday July 21, 2026 | General | JX Wilson | Main Building | Classrooms | Room 03 | Wax (3 coats) | 1 | 3.22
27 | Tuesday July 21, 2026 | General | JX Wilson | Main Building | Classrooms | Room 04 | Wax (3 coats) | 1 | 3.22
27 | Tuesday July 21, 2026 | General | JX Wilson | Multipurpose | Kitchen | Kitchen | Wax (3 coats) | 1 | 2.1
28 | Wednesday July 22, 2026 | General | JX Wilson | Multipurpose | MPR | MPR | Wax (3 coats) | 1 | 16.7
28 | Wednesday July 22, 2026 | General | JX Wilson | Staff & Kinder | Staff | Staff Rooms | Wax (3 coats) | 1 | 7
29 | Thursday July 23, 2026 | General | JX Wilson | Building 13-16 | Classrooms | Room 13 | Deep Clean | 26 | 2.17
29 | Thursday July 23, 2026 | General | JX Wilson | Building 13-16 | Classrooms | Room 14 | Deep Clean | 26 | 2.17
29 | Thursday July 23, 2026 | General | JX Wilson | Building 13-16 | Classrooms | Room 15 | Deep Clean | 26 | 2.1
29 | Thursday July 23, 2026 | General | JX Wilson | Building 13-16 | Classrooms | Room 16 | Deep Clean | 26 | 2.17
29 | Thursday July 23, 2026 | General | JX Wilson | Building 17-19 | Classrooms | Room 17 | Deep Clean | 26 | 2.1
29 | Thursday July 23, 2026 | General | JX Wilson | Building 9-12 | Classrooms | Room 09 | Deep Clean | 26 | 2.25
29 | Thursday July 23, 2026 | General | JX Wilson | Building 9-12 | Classrooms | Room 10 | Deep Clean | 26 | 2.17
29 | Thursday July 23, 2026 | General | JX Wilson | Building 9-12 | Classrooms | Room 11 | Deep Clean | 26 | 2.03
29 | Thursday July 23, 2026 | General | JX Wilson | Building 9-12 | Classrooms | Room 12 | Deep Clean | 26 | 2.17
29 | Thursday July 23, 2026 | General | JX Wilson | Main Building 2 | Classrooms | Room 05 | Deep Clean | 26 | 2.25
29 | Thursday July 23, 2026 | General | JX Wilson | Main Building 2 | Classrooms | Room 06 | Deep Clean | 26 | 2.25
29 | Thursday July 23, 2026 | General | JX Wilson | Main Building 2 | Classrooms | Room 07 | Deep Clean | 26 | 2.25
29 | Thursday July 23, 2026 | General | JX Wilson | Main Building 2 | Classrooms | Room 08 | Deep Clean | 26 | 0.9
30 | Friday July 24, 2026 | General | JX Wilson | Main Building 2 | Classrooms | Room 08 | Deep Clean | 26 | 1.35
30 | Friday July 24, 2026 | General | JX Wilson | Building 13-16 | Classrooms | Room 13 | Strip | 26 | 1.94
30 | Friday July 24, 2026 | General | JX Wilson | Building 13-16 | Classrooms | Room 14 | Strip | 26 | 1.94
30 | Friday July 24, 2026 | General | JX Wilson | Building 13-16 | Classrooms | Room 15 | Strip | 26 | 1.88
30 | Friday July 24, 2026 | General | JX Wilson | Building 13-16 | Classrooms | Room 16 | Strip | 26 | 1.94
30 | Friday July 24, 2026 | General | JX Wilson | Building 17-19 | Classrooms | Room 17 | Strip | 26 | 1.88
30 | Friday July 24, 2026 | General | JX Wilson | Building 9-12 | Classrooms | Room 09 | Strip | 26 | 2.01
30 | Friday July 24, 2026 | General | JX Wilson | Building 9-12 | Classrooms | Room 10 | Strip | 26 | 1.94
30 | Friday July 24, 2026 | General | JX Wilson | Building 9-12 | Classrooms | Room 11 | Strip | 26 | 1.81
30 | Friday July 24, 2026 | General | JX Wilson | Building 9-12 | Classrooms | Room 12 | Strip | 26 | 1.94
30 | Friday July 24, 2026 | General | JX Wilson | Main Building 2 | Classrooms | Room 05 | Strip | 26 | 2.01
30 | Friday July 24, 2026 | General | JX Wilson | Main Building 2 | Classrooms | Room 06 | Strip | 26 | 2.01
30 | Friday July 24, 2026 | General | JX Wilson | Main Building 2 | Classrooms | Room 07 | Strip | 26 | 2.01
30 | Friday July 24, 2026 | General | JX Wilson | Main Building 2 | Classrooms | Room 08 | Strip | 26 | 2.01
31 | Monday July 27, 2026 | General | JX Wilson | Building 13-16 | Classrooms | Room 13 | Wax (3 coats) | 26 | 2.92
31 | Monday July 27, 2026 | General | JX Wilson | Building 13-16 | Classrooms | Room 14 | Wax (3 coats) | 26 | 2.91
31 | Monday July 27, 2026 | General | JX Wilson | Building 13-16 | Classrooms | Room 15 | Wax (3 coats) | 26 | 2.81
31 | Monday July 27, 2026 | General | JX Wilson | Building 13-16 | Classrooms | Room 16 | Wax (3 coats) | 26 | 2.92
31 | Monday July 27, 2026 | General | JX Wilson | Building 17-19 | Classrooms | Room 17 | Wax (3 coats) | 26 | 2.81
31 | Monday July 27, 2026 | General | JX Wilson | Building 9-12 | Classrooms | Room 09 | Wax (3 coats) | 26 | 3.01
31 | Monday July 27, 2026 | General | JX Wilson | Building 9-12 | Classrooms | Room 10 | Wax (3 coats) | 26 | 2.92
31 | Monday July 27, 2026 | General | JX Wilson | Building 9-12 | Classrooms | Room 11 | Wax (3 coats) | 26 | 2.72
31 | Monday July 27, 2026 | General | JX Wilson | Building 9-12 | Classrooms | Room 12 | Wax (3 coats) | 26 | 2.92
32 | Tuesday July 28, 2026 | General | JX Wilson | Main Building 2 | Classrooms | Room 05 | Wax (3 coats) | 26 | 3.01
32 | Tuesday July 28, 2026 | General | JX Wilson | Main Building 2 | Classrooms | Room 06 | Wax (3 coats) | 26 | 3.01
32 | Tuesday July 28, 2026 | General | JX Wilson | Main Building 2 | Classrooms | Room 07 | Wax (3 coats) | 26 | 3.01
32 | Tuesday July 28, 2026 | General | JX Wilson | Main Building 2 | Classrooms | Room 08 | Wax (3 coats) | 26 | 3.01

## Tasks
Site | Building | Zone | Room | Task | Available Day | Available Date | Total Hours | Remaining Hours | Status | Notes
Wright | Elementary | Classrooms | Room 02 | Deep Clean | 1 | Monday June 15, 2026 | 2.1 | 0 | Complete
Wright | Elementary | Classrooms | Room 02 | Strip | 1 | Monday June 15, 2026 | 1.88 | 0 | Complete
Wright | Elementary | Classrooms | Room 02 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.81 | 0 | Complete
Wright | Elementary | Classrooms | Room 03 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 03 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 03 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.91 | 0 | Complete
Wright | Elementary | Classrooms | Room 04 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 04 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 04 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.91 | 0 | Complete
Wright | Elementary | Classrooms | Room 05 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 05 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 05 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.91 | 0 | Complete
Wright | Elementary | Classrooms | Room 06 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 06 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 06 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.91 | 0 | Complete
Wright | Elementary | Classrooms | Room 07 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 07 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 07 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.91 | 0 | Complete
Wright | Elementary | Classrooms | Room 08 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 08 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 08 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.91 | 0 | Complete
Wright | Elementary | Classrooms | Room 09 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 09 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 09 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.91 | 0 | Complete
Wright | Elementary | Classrooms | Room 10 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 10 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 10 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.91 | 0 | Complete
Wright | Elementary | Classrooms | Room 11 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 11 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 11 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.91 | 0 | Complete
Wright | Elementary | Classrooms | Room 12 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 12 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 12 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.91 | 0 | Complete
Wright | Elementary | Classrooms | Room 13 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 13 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 13 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.91 | 0 | Complete
Wright | Elementary | Classrooms | Room 14 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 14 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 14 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.91 | 0 | Complete
Wright | Elementary | Classrooms | Room 15 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 15 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 15 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.91 | 0 | Complete
Wright | Elementary | Classrooms | Room 16 | Deep Clean | 1 | Monday June 15, 2026 | 2.02 | 0 | Complete
Wright | Elementary | Classrooms | Room 16 | Strip | 1 | Monday June 15, 2026 | 1.81 | 0 | Complete
Wright | Elementary | Classrooms | Room 16 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.71 | 0 | Complete
Wright | Elementary | Classrooms | Room 17 | Deep Clean | 1 | Monday June 15, 2026 | 2.1 | 0 | Complete
Wright | Elementary | Classrooms | Room 17 | Strip | 1 | Monday June 15, 2026 | 1.88 | 0 | Complete
Wright | Elementary | Classrooms | Room 17 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.81 | 0 | Complete
Wright | Elementary | Classrooms | Room 18 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 18 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 18 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.92 | 0 | Complete
Wright | Elementary | Classrooms | Room 20 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 20 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 20 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.92 | 0 | Complete
Wright | Elementary | Classrooms | Room 21 | Deep Clean | 1 | Monday June 15, 2026 | 2.1 | 0 | Complete
Wright | Elementary | Classrooms | Room 21 | Strip | 1 | Monday June 15, 2026 | 1.88 | 0 | Complete
Wright | Elementary | Classrooms | Room 21 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.81 | 0 | Complete
Wright | Elementary | Classrooms | Room 22 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 22 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 22 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.92 | 0 | Complete
Wright | Elementary | Classrooms | Room 23 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 23 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 23 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.92 | 0 | Complete
Wright | Elementary | Classrooms | Room 24 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 24 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 24 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.92 | 0 | Complete
Wright | Elementary | Classrooms | Room 25 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 25 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 25 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.92 | 0 | Complete
Wright | Elementary | Classrooms | Room 26 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 26 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 26 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.92 | 0 | Complete
Wright | Elementary | Classrooms | Room 27 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
Wright | Elementary | Classrooms | Room 27 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Elementary | Classrooms | Room 27 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.92 | 0 | Complete
Wright | MPR | Kitchen | Kitchen | Deep Clean | 1 | Monday June 15, 2026 | 2.19 | 0 | Complete
Wright | MPR | Kitchen | Kitchen | Strip | 1 | Monday June 15, 2026 | 2.92 | 0 | Complete
Wright | MPR | Kitchen | Kitchen | Wax (3 coats) | 1 | Monday June 15, 2026 | 4.38 | 0 | Complete
Wright | MPR | MPR | New Gym | Deep Clean | 1 | Monday June 15, 2026 | 7.8 | 0 | Complete
Wright | MPR | MPR | New Gym | Strip | 1 | Monday June 15, 2026 | 10.4 | 0 | Complete
Wright | MPR | MPR | New Gym | Wax (3 coats) | 1 | Monday June 15, 2026 | 15.6 | 0 | Complete
Wright | Main Office Building | Classrooms | Room 1 | Deep Clean | 1 | Monday June 15, 2026 | 2.1 | 0 | Complete
Wright | Main Office Building | Classrooms | Room 1 | Strip | 1 | Monday June 15, 2026 | 1.88 | 0 | Complete
Wright | Main Office Building | Classrooms | Room 1 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.81 | 0 | Complete
Wright | Main Office Building | Classrooms | Room K | Deep Clean | 1 | Monday June 15, 2026 | 2.94 | 0 | Complete
Wright | Main Office Building | Classrooms | Room K | Strip | 1 | Monday June 15, 2026 | 1.3 | 0 | Complete
Wright | Main Office Building | Classrooms | Room K | Wax (3 coats) | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
Wright | Main Office Building | Office | Main Office | Deep Clean | 1 | Monday June 15, 2026 | 4.59 | 0 | Complete
Wright | Old MPR | Kitchen | Old Kitchen | Deep Clean | 1 | Monday June 15, 2026 | 1.16 | 0 | Complete
Wright | Old MPR | MPR | Old Gym | Deep Clean | 1 | Monday June 15, 2026 | 4.75 | 0 | Complete
Wright | Old MPR | MPR | Old Gym | Strip | 1 | Monday June 15, 2026 | 6.33 | 0 | Complete
Wright | Old MPR | MPR | Old Gym | Wax (3 coats) | 1 | Monday June 15, 2026 | 9.5 | 0 | Complete
RL Stevens | Building A | Classrooms | Room 03 | Deep Clean | 1 | Monday June 15, 2026 | 1.96 | 0 | Complete
RL Stevens | Building A | Classrooms | Room 03 | Strip | 1 | Monday June 15, 2026 | 1.75 | 0 | Complete
RL Stevens | Building A | Classrooms | Room 03 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.62 | 0 | Complete
RL Stevens | Building A | Office | Admin Office | Deep Clean | 1 | Monday June 15, 2026 | 2.15 | 0 | Complete
RL Stevens | Building A | Staff | Staff Room | Deep Clean | 1 | Monday June 15, 2026 | 2.97 | 0 | Complete
RL Stevens | Building A | Staff | Staff Room | Strip | 1 | Monday June 15, 2026 | 1.96 | 0 | Complete
RL Stevens | Building A | Staff | Staff Room | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.95 | 0 | Complete
RL Stevens | Building B | Classrooms | K1 | Deep Clean | 1 | Monday June 15, 2026 | 3.22 | 0 | Complete
RL Stevens | Building B | Classrooms | K1 | Strip | 1 | Monday June 15, 2026 | 2.88 | 0 | Complete
RL Stevens | Building B | Classrooms | K1 | Wax (3 coats) | 1 | Monday June 15, 2026 | 4.31 | 0 | Complete
RL Stevens | Building B | Classrooms | K2 | Deep Clean | 1 | Monday June 15, 2026 | 3.45 | 0 | Complete
RL Stevens | Building B | Classrooms | K2 | Strip | 1 | Monday June 15, 2026 | 3.08 | 0 | Complete
RL Stevens | Building B | Classrooms | K2 | Wax (3 coats) | 1 | Monday June 15, 2026 | 4.62 | 0 | Complete
RL Stevens | Building B | Library | Library | Deep Clean | 1 | Monday June 15, 2026 | 3.28 | 0 | Complete
RL Stevens | Building B | Library | Library | Strip | 1 | Monday June 15, 2026 | 1.37 | 0 | Complete
RL Stevens | Building B | Library | Library | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.06 | 0 | Complete
RL Stevens | Building C | Kitchen | Kitchen | Deep Clean | 1 | Monday June 15, 2026 | 2.72 | 0 | Complete
RL Stevens | Building C | Kitchen | Kitchen | Strip | 1 | Monday June 15, 2026 | 3.63 | 0 | Complete
RL Stevens | Building C | Kitchen | Kitchen | Wax (3 coats) | 1 | Monday June 15, 2026 | 5.44 | 0 | Complete
RL Stevens | Building C | MPR | MPR | Deep Clean | 1 | Monday June 15, 2026 | 11.76 | 0 | Complete
RL Stevens | Building C | MPR | MPR | Strip | 1 | Monday June 15, 2026 | 15.68 | 0 | Complete
RL Stevens | Building C | MPR | MPR | Wax (3 coats) | 1 | Monday June 15, 2026 | 23.52 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 14 | Deep Clean | 1 | Monday June 15, 2026 | 2.54 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 14 | Strip | 1 | Monday June 15, 2026 | 2.27 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 14 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.4 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 15 | Deep Clean | 1 | Monday June 15, 2026 | 2.54 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 15 | Strip | 1 | Monday June 15, 2026 | 2.27 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 15 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.4 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 16 | Deep Clean | 1 | Monday June 15, 2026 | 2.54 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 16 | Strip | 1 | Monday June 15, 2026 | 2.27 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 16 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.4 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 17 | Deep Clean | 1 | Monday June 15, 2026 | 2.54 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 17 | Strip | 1 | Monday June 15, 2026 | 2.27 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 17 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.4 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 18 | Deep Clean | 1 | Monday June 15, 2026 | 2.54 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 18 | Strip | 1 | Monday June 15, 2026 | 2.27 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 18 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.4 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 19 | Deep Clean | 1 | Monday June 15, 2026 | 2.54 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 19 | Strip | 1 | Monday June 15, 2026 | 2.27 | 0 | Complete
RL Stevens | Building D | Classrooms | Room 19 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.4 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 08 | Deep Clean | 1 | Monday June 15, 2026 | 2.54 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 08 | Strip | 1 | Monday June 15, 2026 | 2.27 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 08 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.4 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 09 | Deep Clean | 1 | Monday June 15, 2026 | 2.54 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 09 | Strip | 1 | Monday June 15, 2026 | 2.27 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 09 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.4 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 10 | Deep Clean | 1 | Monday June 15, 2026 | 2.54 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 10 | Strip | 1 | Monday June 15, 2026 | 2.27 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 10 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.4 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 11 | Deep Clean | 1 | Monday June 15, 2026 | 2.54 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 11 | Strip | 1 | Monday June 15, 2026 | 2.27 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 11 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.4 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 12 | Deep Clean | 1 | Monday June 15, 2026 | 2.62 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 12 | Strip | 1 | Monday June 15, 2026 | 2.34 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 12 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.51 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 13 | Deep Clean | 1 | Monday June 15, 2026 | 2.54 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 13 | Strip | 1 | Monday June 15, 2026 | 2.27 | 0 | Complete
RL Stevens | Building E | Classrooms | Room 13 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.4 | 0 | Complete
RL Stevens | Building F | Classrooms | Room 04 | Deep Clean | 1 | Monday June 15, 2026 | 2.54 | 0 | Complete
RL Stevens | Building F | Classrooms | Room 04 | Strip | 1 | Monday June 15, 2026 | 2.27 | 0 | Complete
RL Stevens | Building F | Classrooms | Room 04 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.4 | 0 | Complete
RL Stevens | Building F | Classrooms | Room 05 | Deep Clean | 1 | Monday June 15, 2026 | 2.54 | 0 | Complete
RL Stevens | Building F | Classrooms | Room 05 | Strip | 1 | Monday June 15, 2026 | 2.27 | 0 | Complete
RL Stevens | Building F | Classrooms | Room 05 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.4 | 0 | Complete
RL Stevens | Building F | Classrooms | Room 06 | Deep Clean | 1 | Monday June 15, 2026 | 2.54 | 0 | Complete
RL Stevens | Building F | Classrooms | Room 06 | Strip | 1 | Monday June 15, 2026 | 2.27 | 0 | Complete
RL Stevens | Building F | Classrooms | Room 06 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.4 | 0 | Complete
RL Stevens | Building F | Classrooms | Room 07 | Deep Clean | 1 | Monday June 15, 2026 | 2.54 | 0 | Complete
RL Stevens | Building F | Classrooms | Room 07 | Strip | 1 | Monday June 15, 2026 | 2.27 | 0 | Complete
RL Stevens | Building F | Classrooms | Room 07 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.4 | 0 | Complete
RL Stevens | Building H | Classrooms | Room 20 | Deep Clean | 1 | Monday June 15, 2026 | 2.33 | 0 | Complete
RL Stevens | Building H | Classrooms | Room 20 | Strip | 1 | Monday June 15, 2026 | 2.08 | 0 | Complete
RL Stevens | Building H | Classrooms | Room 20 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.12 | 0 | Complete
RL Stevens | Building H | Classrooms | Room 21 | Deep Clean | 1 | Monday June 15, 2026 | 1.81 | 0 | Complete
RL Stevens | Building H | Classrooms | Room 21 | Strip | 1 | Monday June 15, 2026 | 1.62 | 0 | Complete
RL Stevens | Building H | Classrooms | Room 21 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.43 | 0 | Complete
RL Stevens | Building H | Classrooms | Room 22 | Deep Clean | 1 | Monday June 15, 2026 | 2.25 | 0 | Complete
RL Stevens | Building H | Classrooms | Room 22 | Strip | 1 | Monday June 15, 2026 | 2.01 | 0 | Complete
RL Stevens | Building H | Classrooms | Room 22 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.01 | 0 | Complete
RL Stevens | Building H | Office | Conference Room 1 | Deep Clean | 1 | Monday June 15, 2026 | 0.71 | 0 | Complete
RL Stevens | Building H | Office | Conference Room 2 | Deep Clean | 1 | Monday June 15, 2026 | 0.68 | 0 | Complete
RL Stevens | Building I | Classrooms | K3 | Deep Clean | 1 | Monday June 15, 2026 | 2.25 | 0 | Complete
RL Stevens | Building I | Classrooms | K3 | Strip | 1 | Monday June 15, 2026 | 2.01 | 0 | Complete
RL Stevens | Building I | Classrooms | K3 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.01 | 0 | Complete
RL Stevens | Building I | Classrooms | K4 | Deep Clean | 1 | Monday June 15, 2026 | 2.25 | 0 | Complete
RL Stevens | Building I | Classrooms | K4 | Strip | 1 | Monday June 15, 2026 | 2.01 | 0 | Complete
RL Stevens | Building I | Classrooms | K4 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.01 | 0 | Complete
RL Stevens | Building J | Classrooms | Room 01 | Deep Clean | 1 | Monday June 15, 2026 | 2.33 | 0 | Complete
RL Stevens | Building J | Classrooms | Room 01 | Strip | 1 | Monday June 15, 2026 | 2.08 | 0 | Complete
RL Stevens | Building J | Classrooms | Room 01 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.12 | 0 | Complete
RL Stevens | Building J | Classrooms | Room 02 | Deep Clean | 1 | Monday June 15, 2026 | 2.25 | 0 | Complete
RL Stevens | Building J | Classrooms | Room 02 | Strip | 1 | Monday June 15, 2026 | 2.01 | 0 | Complete
RL Stevens | Building J | Classrooms | Room 02 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.01 | 0 | Complete
RL Stevens | Building J | Classrooms | Room 25 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
RL Stevens | Building J | Classrooms | Room 25 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
RL Stevens | Building J | Classrooms | Room 25 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.91 | 0 | Complete
JX Wilson | Building 13-16 | Classrooms | Room 13 | Deep Clean | 26 | Monday July 20, 2026 | 2.17 | 0 | Complete
JX Wilson | Building 13-16 | Classrooms | Room 13 | Strip | 26 | Monday July 20, 2026 | 1.94 | 0 | Complete
JX Wilson | Building 13-16 | Classrooms | Room 13 | Wax (3 coats) | 26 | Monday July 20, 2026 | 2.92 | 0 | Complete
JX Wilson | Building 13-16 | Classrooms | Room 14 | Deep Clean | 26 | Monday July 20, 2026 | 2.17 | 0 | Complete
JX Wilson | Building 13-16 | Classrooms | Room 14 | Strip | 26 | Monday July 20, 2026 | 1.94 | 0 | Complete
JX Wilson | Building 13-16 | Classrooms | Room 14 | Wax (3 coats) | 26 | Monday July 20, 2026 | 2.91 | 0 | Complete
JX Wilson | Building 13-16 | Classrooms | Room 15 | Deep Clean | 26 | Monday July 20, 2026 | 2.1 | 0 | Complete
JX Wilson | Building 13-16 | Classrooms | Room 15 | Strip | 26 | Monday July 20, 2026 | 1.88 | 0 | Complete
JX Wilson | Building 13-16 | Classrooms | Room 15 | Wax (3 coats) | 26 | Monday July 20, 2026 | 2.81 | 0 | Complete
JX Wilson | Building 13-16 | Classrooms | Room 16 | Deep Clean | 26 | Monday July 20, 2026 | 2.17 | 0 | Complete
JX Wilson | Building 13-16 | Classrooms | Room 16 | Strip | 26 | Monday July 20, 2026 | 1.94 | 0 | Complete
JX Wilson | Building 13-16 | Classrooms | Room 16 | Wax (3 coats) | 26 | Monday July 20, 2026 | 2.92 | 0 | Complete
JX Wilson | Building 17-19 | Classrooms | Room 17 | Deep Clean | 26 | Monday July 20, 2026 | 2.1 | 0 | Complete
JX Wilson | Building 17-19 | Classrooms | Room 17 | Strip | 26 | Monday July 20, 2026 | 1.88 | 0 | Complete
JX Wilson | Building 17-19 | Classrooms | Room 17 | Wax (3 coats) | 26 | Monday July 20, 2026 | 2.81 | 0 | Complete
JX Wilson | Building 17-19 | Classrooms | Room 18 | Deep Clean | 1 | Monday June 15, 2026 | 2.25 | 0 | Complete
JX Wilson | Building 17-19 | Classrooms | Room 18 | Strip | 1 | Monday June 15, 2026 | 2.01 | 0 | Complete
JX Wilson | Building 17-19 | Classrooms | Room 18 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.01 | 0 | Complete
JX Wilson | Building 17-19 | Classrooms | Room 19 | Deep Clean | 1 | Monday June 15, 2026 | 2.1 | 0 | Complete
JX Wilson | Building 17-19 | Classrooms | Room 19 | Strip | 1 | Monday June 15, 2026 | 1.88 | 0 | Complete
JX Wilson | Building 17-19 | Classrooms | Room 19 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.81 | 0 | Complete
JX Wilson | Building 20-22 & 27 | Classrooms | Room 20 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
JX Wilson | Building 20-22 & 27 | Classrooms | Room 20 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
JX Wilson | Building 20-22 & 27 | Classrooms | Room 20 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.92 | 0 | Complete
JX Wilson | Building 20-22 & 27 | Classrooms | Room 21 | Deep Clean | 1 | Monday June 15, 2026 | 2.17 | 0 | Complete
JX Wilson | Building 20-22 & 27 | Classrooms | Room 21 | Strip | 1 | Monday June 15, 2026 | 1.94 | 0 | Complete
JX Wilson | Building 20-22 & 27 | Classrooms | Room 21 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.92 | 0 | Complete
JX Wilson | Building 20-22 & 27 | Classrooms | Room 22 | Deep Clean | 1 | Monday June 15, 2026 | 2.1 | 0 | Complete
JX Wilson | Building 20-22 & 27 | Classrooms | Room 22 | Strip | 1 | Monday June 15, 2026 | 1.88 | 0 | Complete
JX Wilson | Building 20-22 & 27 | Classrooms | Room 22 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.81 | 0 | Complete
JX Wilson | Building 20-22 & 27 | Classrooms | Room 27 | Deep Clean | 1 | Monday June 15, 2026 | 2.1 | 0 | Complete
JX Wilson | Building 20-22 & 27 | Classrooms | Room 27 | Strip | 1 | Monday June 15, 2026 | 1.88 | 0 | Complete
JX Wilson | Building 20-22 & 27 | Classrooms | Room 27 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.81 | 0 | Complete
JX Wilson | Building 23-26 | Classrooms | Room 23 | Deep Clean | 1 | Monday June 15, 2026 | 2.66 | 0 | Complete
JX Wilson | Building 23-26 | Classrooms | Room 23 | Strip | 1 | Monday June 15, 2026 | 2.38 | 0 | Complete
JX Wilson | Building 23-26 | Classrooms | Room 23 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.56 | 0 | Complete
JX Wilson | Building 23-26 | Classrooms | Room 24 | Deep Clean | 1 | Monday June 15, 2026 | 1.96 | 0 | Complete
JX Wilson | Building 23-26 | Classrooms | Room 24 | Strip | 1 | Monday June 15, 2026 | 1.75 | 0 | Complete
JX Wilson | Building 23-26 | Classrooms | Room 24 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.62 | 0 | Complete
JX Wilson | Building 23-26 | Classrooms | Room 25 | Deep Clean | 1 | Monday June 15, 2026 | 2.03 | 0 | Complete
JX Wilson | Building 23-26 | Classrooms | Room 25 | Strip | 1 | Monday June 15, 2026 | 1.81 | 0 | Complete
JX Wilson | Building 23-26 | Classrooms | Room 25 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.72 | 0 | Complete
JX Wilson | Building 23-26 | Classrooms | Room 26 | Deep Clean | 1 | Monday June 15, 2026 | 1.96 | 0 | Complete
JX Wilson | Building 23-26 | Classrooms | Room 26 | Strip | 1 | Monday June 15, 2026 | 1.75 | 0 | Complete
JX Wilson | Building 23-26 | Classrooms | Room 26 | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.62 | 0 | Complete
JX Wilson | Building 9-12 | Classrooms | Room 09 | Deep Clean | 26 | Monday July 20, 2026 | 2.25 | 0 | Complete
JX Wilson | Building 9-12 | Classrooms | Room 09 | Strip | 26 | Monday July 20, 2026 | 2.01 | 0 | Complete
JX Wilson | Building 9-12 | Classrooms | Room 09 | Wax (3 coats) | 26 | Monday July 20, 2026 | 3.01 | 0 | Complete
JX Wilson | Building 9-12 | Classrooms | Room 10 | Deep Clean | 26 | Monday July 20, 2026 | 2.17 | 0 | Complete
JX Wilson | Building 9-12 | Classrooms | Room 10 | Strip | 26 | Monday July 20, 2026 | 1.94 | 0 | Complete
JX Wilson | Building 9-12 | Classrooms | Room 10 | Wax (3 coats) | 26 | Monday July 20, 2026 | 2.92 | 0 | Complete
JX Wilson | Building 9-12 | Classrooms | Room 11 | Deep Clean | 26 | Monday July 20, 2026 | 2.03 | 0 | Complete
JX Wilson | Building 9-12 | Classrooms | Room 11 | Strip | 26 | Monday July 20, 2026 | 1.81 | 0 | Complete
JX Wilson | Building 9-12 | Classrooms | Room 11 | Wax (3 coats) | 26 | Monday July 20, 2026 | 2.72 | 0 | Complete
JX Wilson | Building 9-12 | Classrooms | Room 12 | Deep Clean | 26 | Monday July 20, 2026 | 2.17 | 0 | Complete
JX Wilson | Building 9-12 | Classrooms | Room 12 | Strip | 26 | Monday July 20, 2026 | 1.94 | 0 | Complete
JX Wilson | Building 9-12 | Classrooms | Room 12 | Wax (3 coats) | 26 | Monday July 20, 2026 | 2.92 | 0 | Complete
JX Wilson | Main Building | Classrooms | Room 01 | Deep Clean | 1 | Monday June 15, 2026 | 2.4 | 0 | Complete
JX Wilson | Main Building | Classrooms | Room 01 | Strip | 1 | Monday June 15, 2026 | 2.15 | 0 | Complete
JX Wilson | Main Building | Classrooms | Room 01 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.22 | 0 | Complete
JX Wilson | Main Building | Classrooms | Room 03 | Deep Clean | 1 | Monday June 15, 2026 | 2.4 | 0 | Complete
JX Wilson | Main Building | Classrooms | Room 03 | Strip | 1 | Monday June 15, 2026 | 2.15 | 0 | Complete
JX Wilson | Main Building | Classrooms | Room 03 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.22 | 0 | Complete
JX Wilson | Main Building | Classrooms | Room 04 | Deep Clean | 1 | Monday June 15, 2026 | 2.4 | 0 | Complete
JX Wilson | Main Building | Classrooms | Room 04 | Strip | 1 | Monday June 15, 2026 | 2.15 | 0 | Complete
JX Wilson | Main Building | Classrooms | Room 04 | Wax (3 coats) | 1 | Monday June 15, 2026 | 3.22 | 0 | Complete
JX Wilson | Main Building | Office | Main Office | Deep Clean | 1 | Monday June 15, 2026 | 2.57 | 0 | Complete
JX Wilson | Main Building | Office | Principal Office | Deep Clean | 1 | Monday June 15, 2026 | 0.89 | 0 | Complete
JX Wilson | Main Building 2 | Classrooms | Room 05 | Deep Clean | 26 | Monday July 20, 2026 | 2.25 | 0 | Complete
JX Wilson | Main Building 2 | Classrooms | Room 05 | Strip | 26 | Monday July 20, 2026 | 2.01 | 0 | Complete
JX Wilson | Main Building 2 | Classrooms | Room 05 | Wax (3 coats) | 26 | Monday July 20, 2026 | 3.01 | 0 | Complete
JX Wilson | Main Building 2 | Classrooms | Room 06 | Deep Clean | 26 | Monday July 20, 2026 | 2.25 | 0 | Complete
JX Wilson | Main Building 2 | Classrooms | Room 06 | Strip | 26 | Monday July 20, 2026 | 2.01 | 0 | Complete
JX Wilson | Main Building 2 | Classrooms | Room 06 | Wax (3 coats) | 26 | Monday July 20, 2026 | 3.01 | 0 | Complete
JX Wilson | Main Building 2 | Classrooms | Room 07 | Deep Clean | 26 | Monday July 20, 2026 | 2.25 | 0 | Complete
JX Wilson | Main Building 2 | Classrooms | Room 07 | Strip | 26 | Monday July 20, 2026 | 2.01 | 0 | Complete
JX Wilson | Main Building 2 | Classrooms | Room 07 | Wax (3 coats) | 26 | Monday July 20, 2026 | 3.01 | 0 | Complete
JX Wilson | Main Building 2 | Classrooms | Room 08 | Deep Clean | 26 | Monday July 20, 2026 | 2.25 | 0 | Complete
JX Wilson | Main Building 2 | Classrooms | Room 08 | Strip | 26 | Monday July 20, 2026 | 2.01 | 0 | Complete
JX Wilson | Main Building 2 | Classrooms | Room 08 | Wax (3 coats) | 26 | Monday July 20, 2026 | 3.01 | 0 | Complete
JX Wilson | Multipurpose | Kitchen | Kitchen | Deep Clean | 1 | Monday June 15, 2026 | 1.05 | 0 | Complete
JX Wilson | Multipurpose | Kitchen | Kitchen | Strip | 1 | Monday June 15, 2026 | 1.4 | 0 | Complete
JX Wilson | Multipurpose | Kitchen | Kitchen | Wax (3 coats) | 1 | Monday June 15, 2026 | 2.1 | 0 | Complete
JX Wilson | Multipurpose | MPR | MPR | Deep Clean | 1 | Monday June 15, 2026 | 8.35 | 0 | Complete
JX Wilson | Multipurpose | MPR | MPR | Strip | 1 | Monday June 15, 2026 | 11.13 | 0 | Complete
JX Wilson | Multipurpose | MPR | MPR | Wax (3 coats) | 1 | Monday June 15, 2026 | 16.7 | 0 | Complete
JX Wilson | Staff & Kinder | Staff | Staff Rooms | Deep Clean | 1 | Monday June 15, 2026 | 7 | 0 | Complete
JX Wilson | Staff & Kinder | Staff | Staff Rooms | Strip | 1 | Monday June 15, 2026 | 4.67 | 0 | Complete
JX Wilson | Staff & Kinder | Staff | Staff Rooms | Wax (3 coats) | 1 | Monday June 15, 2026 | 7 | 0 | Complete